## Test Execution Summary
<US_7683 As a user who has access to update user role, I should be able to update a user role>
| Tester: Sachini | Release #: <> | Environment - Test & Staging
Test Summery
# | Description | Executed TC # |  |  | # of Defects | Comment
|  | Total | Executed | Not Execued
7683 | As a user who has access to update user role, I should be able to update a user role | 5 | 0 | 5 | 0
Traceability Metrix
Story Point # | Story Description | Test case ID | Test scenario
|  | US_7683_001 | Successfully able to update a new user role
|  | US_7683_002 | Successfully able to update a new user role-with multiple user role permission
|  | US_7683_003 | Unable to update new user role-empty user role name
|  | US_7683_004 | Unable to update new user role-empty permission
|  | US_7683_005 | Unable to update new user role-duplicate user role name
Known Issues
Def# | Description | Status

## Main test cases
Quality Assurance Test Cases (SQATC)
CLIENT CONFIDENTIAL Template ID:SQA-FRM-003 Copyright © 2018
Project Code/Name | Facets |  |  |  |  | Test Cases Summary(Test env.) |  |  |  | Test Cases Summary(Staging env.)
Author | Sachini |  |  |  |  | Status | Smoke test Status | Function test Status |  | Status | Function test Status
Date Created | 2023-08-14 |  |  |  |  | Pass | 0 | 0 |  | Pass | 0
Last Updated on | [5 empty] | Fail | 0 | 0 |  | Fail | 0
Last Updated by | [5 empty] | On Hold | 0 | 0 |  | On Hold | 0
Document References | [5 empty] | Not Executed | 0 |  |  | Not Executed |  |  |  | Yes
Test Objective | update a new user role |  |  |  |  | Not Applicable | 0 | 0 |  | Not Applicable | 0 |  |  | No
** Priority Level 1 consider for smoke test | [5 empty] | Total | 0 | 0 |  | Total | 0
TC_ID | Senario Description | Pre-requisite | Steps | Test Data | Expected Result | Test Result (Smoke Test) | Test Result (Test env.) | Test Result (Staging env.) | Defect ID | Positive / Negative / UI | Severity | Smoke test cases?(Y/N) | Regression Priority Level
US_7683 As a user who has access to update user role, I should be able to update a user role
US_7683_001 | Successfully able to update a new user role | 1. User must be logging to the user creation screen | Open the user management screen |  | User should be able to open the website & It should be go to user management screen | ? | ? | Not Executed |  | Positive | High | Yes
|  |  | Click on the users section |  | User should able to Click on the user section
|  |  | Click on the user role add button |  | User should able to Click on the +user role button
|  |  | Change the correct user role name |  | User should able to change the user role name
|  |  | Change the permission |  | User should able to change the permission
|  |  | Click update button |  | User should able to click Update button
|  |  | Verify the behaviour |  | The system must be thrown a message like "User role update successfully"
US_7683_002 | Successfully able to update a new user role-with multiple user role permission | 1. User must be logging to the user creation screen | Open the user management screen |  | User should be able to open the website & It should be go to user management screen | ? | ? | Not Executed |  | Positive | High | Yes
|  |  | Click on the users section |  | User should able to Click on the user section
|  |  | Click on the user role add button |  | User should able to Click on the +user role button
|  |  | Change the correct user role name |  | User should able to change the user role name
|  |  | Change the multiple permission |  | User should able to change the multiple permission
|  |  | Click update button |  | User should able to click Update button
|  |  | Verify the behaviour |  | The system must be thrown a message like "User role update successfully"
US_7683_003 | Unable to update new user role-empty user role name | 1. User must be logging to the user creation screen | User role name field as empty |  | User should not able to continue the save without give the user name | Not Executed | Not Executed | Not Executed |  | Negative | High | No
|  |  | Verify the error message |  | The system must be thrown an error message like "user role name is required"
User should able to click Sign In button
The system must be thrown an error message like "password is invalid"
US_7683_004 | Unable to update new user role-empty permission | 1. User must be logging to the user creation screen | Permission as empty |  | User should not able to continue the save without give the permission | Not Executed | Not Executed | Not Executed |  | Negative | High | No
|  |  | Verify the error message |  | The system must be thrown an error message like "permission is required"
US_7683_005 | Unable to update new user role-duplicate user role name | 1. User must be logging to the user creation screen | Enter same user role name |  | User should be able to enter the same user role name | Not Executed | Not Executed | Not Executed |  | Negative | High | No
|  |  | Verify the error message |  | The system must be thrown an error message like "User role name is duplicated"

## ReUsable test cases
Quality Assurance Test Cases (SQATC)
CLIENT CONFIDENTIAL Template ID:SQA-FRM-003 Copyright © 2018
Author | [5 empty] | Test Cases Summary(1st round) |  |  | Test Cases Summary(2nd round)
Date Created | [5 empty] | Pass |  |  | Not Executed
Last Updated on | [5 empty] | Fail |  |  | Fail | 0
Last Updated by | [5 empty] | On Hold |  |  | On Hold | 0
[6 empty] | Not Executed |  |  | Not Executed
[6 empty] | Not Applicable | 0 |  | Not Applicable | 0
[6 empty] | Total | 0 |  | Total
TC_ID | Senario Description | Pre-requisite | Steps | Test Data | Expected Result | Test Result (1st round) | Test Result (2nd round) | Defect ID | Positive / Negative / UI | Severity
Login Functionality
ReUse_001 | [5 empty] | Not Executed | Not Executed |  | Positive | High
ReUse_002 | [5 empty] | Not Executed | Not Executed |  | UI | Low
ReUse_003 | [5 empty] | Not Executed | Not Executed |  | Positive | High
ReUse_004 | [5 empty] | Not Executed | Not Executed |  | Positive | High
ReUse_005 | [5 empty] | Not Executed | Not Executed |  | Positive | High
ReUse_006 | [5 empty] | Not Executed | Not Executed |  | Positive | High
ReUse_007 | [5 empty] | Not Executed | Not Executed |  | Negative | Medium
ReUse_008 | [5 empty] | Not Executed | Not Executed |  | Negative | Medium
ReUse_009 | [5 empty] | Not Executed | Not Executed |  | Negative | Medium
ReUse_010 | [5 empty] | Not Executed | Not Executed |  | Negative | Medium
ReUse_011 | [5 empty] | Not Executed | Not Executed |  | Negative | Medium
ReUse_012 | [5 empty] | Not Executed | Not Executed |  | Negative | Medium

## Validation table
Quality Assurance Test Cases (SQATC)
CLIENT CONFIDENTIAL Template ID:SQA-FRM-003 Copyright © 2018
Validation table No 1
Test case ID <ID 1> Validation for Subscription Type
ID | Variable | Test results
1 |  | Not Executed
2 |  | Not Executed
3 |  | Not Executed
Test case ID <ID 2> Validation for Subscription Type
ID | Variable | Test results
1 |  | Not Executed
2 |  | Not Executed
3 |  | Not Executed
Test case ID <ID 3> Validation for Subscription Type
ID | Variable | Test results
1 |  | Not Executed
2 |  | Not Executed
3 |  | Not Executed

## Test Data
Quality Assurance Test Cases (SQATC)
CLIENT CONFIDENTIAL Template ID:SQA-FRM-003 Copyright © 2018
# | Description | Test Data 1 | Test Data 2 | Test Data 3